## 1- General Information
Issued: 25-Jul-2019
F-PM10321 | INFORMATION FOR PROJECT SET UP
1- General Information
to be completed by Finance Officer
Date
Information Supplied by
Project Number
Project Name | Consultancy for “Design, Preparation of Bid Documents & Evaluation of Bids for the Proposed Construction of 400 MLD Capacity Seawater Reverse Osmosis Desalination Plant at Perur along East Coast Road, South of Chennai, Tamil Nadu and Construction Management & Supervision for the Proposed Desalination Plant and its Product Water Conveyance Pipeline from the Plant and upto Porur and all allied works
Project Manager | << to be decided>>
Project Director | Srinivasrao Sunkerla
Class (choose from list) | Project
Location (choose from list) |  | Chennai, Tamilnadu; India
Project Type (choose from list) | Inputs based
Industry Type (choose from list) | Utilities
Funding Source (choose from list) | Foreign Aid or Development Agencies
Work Type (Enter Details) | PMC consultancy services - 400 MLD Desalination plant
Services (choose from list) | Project Mgmt | Includes Design, Tendering, Construction Supervision etc.
Project Description | The objectives of the Consulting Services are to achieve efficient and proper preparation and implementation of the Project through: Design works(CP1, CP2 and CP4), Bid document preparation and Tender assistance (CP1, CP2 and CP4), Construction supervision including defect notification period (CP1, CP2, CP3 and CP4), Facilitation of implementation of Environmental Management Plan (EMP) and Environmental Monitoring Plan (EMoP) (CP1, CP2, CP3,CP4 and CP5), Capacity development, organizational improvement and public awareness activities.
SMEC's Role On The Project | SMEC International - Lead Bidder, SMEC India - JV Member
Confidential? (tick this box if the project details shall not be used for marketing purposes) | Yes, We might need to take prior approval from client allowing use for marketing purpose
Invite come through ECS (Engineering Consulting Scheme)
In order to determine whether there are any Research and Development Tax incentives, might learnings from this extend SMEC’s general knowledge base in this industry? Refer to guidance in G-FIN40001. | No - Research and Devlopment (R&D)
Start Date | 2020-01-02 | Likely date to commence
End Date | 2027-04-30 | Likely date to completion (89 month assignment)
Client's contact details
Customer Name (legal entity we will invoice) | Chennai Metropolitan Water Supply & Sewerage Board (CMWSSB)
Customer contact (person to deal with & title) | Er. P. Rajaram, Superitending Engineer (Desal), CMWSSB
Customer phones (landline and mobile) | 0442845130015, Mobile : 8144930989
Customer fax
Customer address | No.1 Pumping Station Road, Chintadripet, Chennai-600002
Customer email Address | sedesalwing@gmail.com
Funding Agency | JICA
Ultimate Customer Name | CMWSSB
Other information
Opportunity Number (n/a if minor project) | 16100912
Region | India (SAME region)
Office (choose from list) | Other- Not listed | India
Function (choose from list) | WI - WATER INFRASTRUCTURE
Stream (choose from list) | WI URI WATER INFRASTR.
Org unit (no entry needed) | WIURIURI
Org Code (no entry needed)
Purchase Order/Clients reference (if available) | Letter of Acceptance dated 6th Nov 2019
| SMEC International (US$) | SMEC India
|  | US$ | INR
Fee Revenue (US$) | 6390313 | 869642 | 72324600
Reimbursable Revenue (US$) | 120000 |  | 39496000
TOTAL
Cost Plan | Please complete the second worksheet (2-Cost Plan)
Subtasks | Task Name
Mentioned under Cost plan
Other documents needed
Contract | Letter of Acceptance dated 6th Nov 2019
PDS | Yet to be created after signing the agreement
Proposal | Yes
PMP | Draft PMP
Risk Spreadsheet | Part of PMP
Environmental Aspect F-ENV10101 | Attached
Comments/ Additional Details
No

## 2- Cost Plan
INFORMATION FOR PROJECT SET UP
2- Cost Plan
Fixed Price Projects
Time (planned hours for each resource) - names not position! |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89
Role | Name | Total Hours
Total Hours | time axis 2020-03-02 to 2027-07-24
Project Manager | Dr Pararajasegram Dharmabalan | [91 empty] | 0
Water Supply Engineer | Shane Farquharson | [91 empty] | 0
Mechanical Engineer (Desal) | Michael Morillon | [91 empty] | 0
Electrical Engineer (Desal) | Sergio de Bastos Vilar Magalhaes Paulo | [91 empty] | 0
Pipeline Engineer | John Goullee | [91 empty] | 0
Contract Specialist (Desal) | Roderick Mackenzie
Monitoring and Control Expert (Desal) | Manikandan Ganesh Shoranur
Expenses (other expenses likely to be incurred such as airfares, transport, accom. etc) | SMEC International Pty. Ltd. | 2020-03-02: SMEC (India) Private Limited
| US$ | 2020-03-02: US$; 2020-04-01: INR; 2020-05-01: Approx. AUD
Fees (US$) | 6390313 | 2020-03-02: 869642; 2020-04-01: 72324600; 2020-05-01: 9393760.11; 2020-05-31: 1278373.74; 2020-06-30: 1489886.76; 2020-07-30: 12162020.61
Reimbursable
INTERNATIONAL AIRFARES (US$) | 120000 | 2020-06-30: CP1 & CP2; 2020-08-29: CP3; 2020-10-28: CP4; 2020-12-27: CP5; 2021-02-25: TOTAL
TRANSPORT |  | 2020-04-01: 9300000; 2020-06-30: Design; 2020-07-30: CS; 2020-08-29: Design; 2020-09-28: CS; 2020-10-28: Design; 2020-11-27: CS; 2020-12-27: Design; 2021-01-26: CS
LOCAL AIR TRAVEL |  | 2020-04-01: 1000000; 2020-05-01: SMEC International (US$); 2020-06-30: 1174370; 2020-07-30: 1653293; 2020-08-29: 0; 2020-09-28: 1602714; 2020-10-28: 444972; 2020-11-27: 1250562; 2020-12-27: 0; 2021-01-26: 264402; 2021-02-25: 6390313
OFFICE RENT (REIMBURSABLE) - FIXED |  | 2020-04-01: 7700000; 2020-05-01: SMEC India (US$); 2020-06-30: 148518; 2020-07-30: 551636; 2020-08-29: 0; 2020-09-28: 28890; 2020-10-28: 32742; 2020-11-27: 78966; 2020-12-27: 4815; 2021-01-26: 24075; 2021-02-25: 869642
OFFICE SUPPLIES, UTILITIES & COMMUNICATION (REIMBURSABLE) - FIXED |  | 2020-04-01: 2772000; 2020-05-01: SMEC India (INR); 2020-06-30: 7859280; 2020-07-30: 19432560; 2020-08-29: 1830150; 2020-09-28: 23608935; 2020-10-28: 3852030; 2020-11-27: 9447060; 2020-12-27: 2730150; 2021-01-26: 3564435; 2021-02-25: 72324600
OFFICE FURNITURE & EQUIPMENT (REIMBURSABLE) |  | 2020-04-01: 8000000
REPORTS & DOCUMENT PRINTING - FIXED |  | 2020-04-01: 1424000
SURVEYS & INVESTIGATIONS |  | 2020-04-01: 5000000
PER-DIEM ALLOWANCES-FIXED |  | 2020-04-01: 4300000
TOTAL REVENUE (excl. GST) | 6510313 | 2020-03-02: 869642; 2020-04-01: 111820600
= Fees + Disbursements | bar: 2020-03-02 to 2020-04-01
Time and Material Projects
Mark up on expenses (if T&M)
Charge out rates (if T&M)
Please Review and complete relevant fields on the first worksheet (1-General Information) before submission to finance

## SMEC Intl. Fee
|  | Total Billing | Biiling Rate | DESIGN including Tendering (Input months) |  |  |  | Cost (US$) | Construction Supervision including DLP |  |  |  | Cost | Input Months | Cost Check
Role | Name | Cost (US$) | USD | CP1& CP2 | CP3 | CP4 | CP5 |  | CP1&CP2 | CP3 | CP4 | CP5
Project Manager | Dr Pararajasegram Dharmabalan | 2625070 | 37500 | 8 | 0 | 6 | 0 | 525014 | 20 | 12 | 18 | 6 | 2100056 | 70 | 2625000
Water Supply Engineer | Shane Farquharson | 583280 | 25360 | 5 | 0 | 6 | 0 | 278960 | 0 | 0 | 12 |  | 304320 | 23 | 583280
Mechanical Engineer (Desal) | Michael Morillon | 660000 | 44000 | 5 | 0 | 0 | 0 | 220000 | 10 |  |  |  | 440000 | 15 | 660000
Electrical Engineer (Desal) | Sergio de Bastos Vilar Magalhaes Paulo | 328300 | 13132 | 7 |  |  |  | 91924 | 15 |  |  | 3 | 236376 | 25 | 328300
Pipeline Engineer | John Goullee | 1582140 | 22602 | 1 | 0 | 3 |  | 90408 | 3 | 51 | 12 |  | 1491732 | 70 | 1582140
Contract Specialist (Desal) | Roderick Mackenzie | 399663 | 44407 | 8 |  |  |  | 355256 | 1 |  |  |  | 44407 | 9 | 399663
Monitoring and Control Expert (Desal) | Manikandan Ganesh Shoranur | 211860 | 19260 | 3 |  |  |  | 57780 | 8 |  |  |  | 154080 | 11 | 211860
|  | 6390313 | [5 empty] | 1619342 |  |  |  |  | 4770971 |  | 6390313

## SMEC India Fee
|  |  |  | DESIGN including Tendering |  |  |  | Cost (US$) | Cost (INR) | Construction Supervision including DLP |  |  |  | Cost (US$) | Cost (INR) | Input Months | Billing Rate |  | Cost Check
Role | Name | Cost (US$) | Cost (INR) | CP1& CP2 | CP3 | CP4 | CP5 |  |  | CP1&CP2 | CP3 | CP4 | CP5 |  |  |  | (US$) | (INR) | US$ | INR
Civil and Structure Engineer (Desal) | Dr. D. Elancherian | 457590 |  | 6 |  |  |  | 65370 |  | 36 |  |  |  | 392220 |  | 42 | 10895 |  | 457590
Monitoring and Control Expert (Distribution) | Ashish Gosain | 92448 |  | 2 |  | 3 |  | 38520 |  | 3 |  | 4 |  | 53928 |  | 12 | 7704 |  | 92448
Specification Specialist (Desal) | Sethuraman | 29056 |  | 3 |  |  |  | 21792 |  | 1 |  |  |  | 7264 |  | 4 | 7264 |  | 29056
Financial expert | Hemanth Chadda | 36318 |  | 3 |  |  |  | 36318 | [5 empty] | 0 |  | 3 | 12106 |  | 36318
Commissioning Engineer | Santhosh Kumar | 100150 |  | 0 |  |  |  | 0 |  | 10 |  |  |  | 100150 |  | 10 | 10015 |  | 100150
Social Communication Specialist | Rajesh Mishra | 154080 |  | 1 | 0 | 1 | 0.5 | 24075 |  | 3 | 3 | 5 | 2.5 | 130005 |  | 16 | 9630 |  | 154080
Civil Engineer | Ramesh Senthil |  | 31374000 | 6 | 0 | 3 |  |  | 3921750 | 6 | 45 | 12 |  |  | 27452250 | 72 |  | 435750 |  | 31374000
Construction Planner Cost Estimator | Naisa Sreenivasulu Reddy |  | 1200000 | 4 |  |  |  |  | 1200000 | [5 empty] | 0 | 4 |  | 300000 |  | 1200000
Quantity Surveyor - 1 | Vinod Chandra K C |  | 15000000 | 5 |  |  | 3 |  | 2400000 | 42 |  |  |  |  | 12600000 | 50 |  | 300000 |  | 15000000
Secretary | TBN |  | 3660300 | 6 | 5 | 6 | 5 |  | 1150380 | 12 | 12 | 12 | 12 |  | 2509920 | 70 |  | 52290 |  | 3660300
Contract management Specialist | TBN |  | 2614500 | [5 empty] | 0 | 2 | 1.5 | 2 | 0.5 |  | 2614500 | 6 |  | 435750 |  | 2614500
Geo Technical Engineer | TBN |  | 2614500 | 2 | 1 | 2 | 1 |  | 2614500 | [5 empty] | 0 | 6 |  | 435750 |  | 2614500
Office boy-1 | TBN |  | 1830150 | 6 | 5 | 6 | 5 |  | 575190 | 12 | 12 | 12 | 12 |  | 1254960 | 70 |  | 26145 |  | 1830150
Office boy-2 | TBN |  | 1830150 | 6 | 5 | 6 | 5 |  | 575190 | 12 | 12 | 12 | 12 |  | 1254960 | 70 |  | 26145 |  | 1830150
Office Manager & Travel & Visa processing officer | TBN |  | 7320600 | 6 | 5 | 6 | 5 |  | 2300760 | 12 | 12 | 12 | 12 |  | 5019840 | 70 |  | 104580 |  | 7320600
Accountant | TBN |  | 4880400 | 6 | 5 | 6 | 5 |  | 1533840 | 12 | 12 | 12 | 12 |  | 3346560 | 70 |  | 69720 |  | 4880400
|  | 869642 | 72324600 |  |  |  |  | 186075 | 16271610 |  |  |  |  | 683567 | 56052990
[14 empty] | 869642 | 72324600

## CP 1&CP 2
CP1 Desalination Plant and CP2 Pumping Stations and Reservoirs
[5 empty] | Design + Tendering |  |  |  | Construction Supervision +DLP
Role | Name | Cost (US$) | Cost (INR) | Total Months | Input in CP1&CP2 | SMEC Intl (US$) | SMEC India (US$) | SMEC India (INR) | Input in CP1 & CP2 | SMEC Intl (US$) | SMEC India (US$) | SMEC India (INR)
Project Manager | Dr Pararajasegram Dharmabalan | 2625070 |  | 70 | 8 | 300008 |  |  | 20 | 750020
Water Supply Engineer | Shane Farquharson | 583280 |  | 23 | 5 | 126800 |  |  | 0 | 0
Mechanical Engineer (Desal) | Michael Morillon | 660000 |  | 15 | 5 | 220000 |  |  | 10 | 440000
Electrical Engineer (Desal) | Sergio de Bastos Vilar Magalhaes Paulo | 328300 |  | 25 | 7 | 91924 |  |  | 15 | 196980
Pipeline Engineer | John Goullee | 1582140 |  | 70 | 1 | 22602 |  |  | 3 | 67806
Contract Specialist (Desal) | Roderick Mackenzie | 399663 |  | 9 | 8 | 355256 |  |  | 1 | 44407
Monitoring and Control Expert (Desal) | Manikandan Ganesh Shoranur | 211860 |  | 11 | 3 | 57780 |  |  | 8 | 154080
Civil and Structure Engineer (Desal) | Dr. D. Elancherian | 457590 |  | 42 | 6 |  | 65370 |  | 36 |  | 392220
Monitoring and Control Expert (Distribution) | Ashish Gosain | 92448 |  | 12 | 2 |  | 15408 |  | 3 |  | 23112
Specification Specialist (Desal) | Shanmuga Nathan J. | 29056 |  | 4 | 3 |  | 21792 |  | 1 |  | 7264
Financial expert | Hemanth Chadda | 36318 |  | 3 | 3 |  | 36318 |  | 0 |  | 0
Commissioning Engineer | Santhosh Kumar | 100150 |  | 10 | 0 |  | 0 |  | 10 |  | 100150
Social Communication Specialist | Rajesh Mishra | 154080 |  | 16 | 1 |  | 9630 |  | 3 |  | 28890
Civil Engineer | Ramesh Senthil |  | 31374000 | 72 | 6 |  |  | 2614500 | 6 |  |  | 2614500
Construction Planner Cost Estimator | Naisa Sreenivasulu Reddy |  | 1200000 | 4 | 4 |  |  | 1200000 | 0 |  |  | 0
Quantity Surveyor - 1 | Vinod Chandra K C |  | 15000000 | 50 | 5 |  |  | 1500000 | 42 |  |  | 12600000
Secretary | TBN |  | 3660300 | 70 | 6 |  |  | 313740 | 12 |  |  | 627480
Contract management Specialist | TBN |  | 2614500 | 6 | 0 |  |  | 0 | 2 |  |  | 871500
Geo Technical Engineer | TBN |  | 2614500 | 6 | 2 |  |  | 871500 | 0 |  |  | 0
Office boy-1 | TBN |  | 1830150 | 70 | 6 |  |  | 156870 | 12 |  |  | 313740
Office boy-2 | TBN |  | 1830150 | 70 | 6 |  |  | 156870 | 12 |  |  | 313740
Office Manager & Travel & Visa processing officer | TBN |  | 7320600 | 70 | 6 |  |  | 627480 | 12 |  |  | 1254960
Accountant | TBN |  | 4880400 | 70 | 6 |  |  | 418320 | 12 |  |  | 836640
|  | 7259955 | 72324600 |  |  | 1174370 | 148518 | 7859280 |  | 1653293 | 551636 | 19432560

## CP 3
CP1 Desalination Plant and CP2 Pumping Stations and Reservoirs
[5 empty] | Design + Tendering |  |  |  | Construction Supervision +DLP
Role | Name | Cost (US$) | Cost (INR) | Total Months | Input in CP3 | SMEC Intl (US$) | SMEC India (US$) | SMEC India (INR) | Input in CP3 | SMEC Intl (US$) | SMEC India (US$) | SMEC India (INR)
Project Manager | Dr Pararajasegram Dharmabalan | 2625070 |  | 70 | 0 | 0 |  |  | 12 | 450012
Water Supply Engineer | Shane Farquharson | 583280 |  | 23 | 0 | 0 |  |  | 0 | 0
Mechanical Engineer (Desal) | Michael Morillon | 660000 |  | 15 | 0 | 0 |  |  | 0 | 0
Electrical Engineer (Desal) | Sergio de Bastos Vilar Magalhaes Paulo | 328300 |  | 25 | 0 | 0 |  |  | 0 | 0
Pipeline Engineer | John Goullee | 1582140 |  | 70 | 0 | 0 |  |  | 51 | 1152702
Contract Specialist (Desal) | Roderick Mackenzie | 399663 |  | 9 | 0 | 0 |  |  | 0 | 0
Monitoring and Control Expert (Desal) | Manikandan Ganesh Shoranur | 211860 |  | 11 | 0 | 0 |  |  | 0 | 0
Civil and Structure Engineer (Desal) | Dr. D. Elancherian | 457590 |  | 42 | 0 |  | 0 |  | 0 |  | 0
Monitoring and Control Expert (Distribution) | Ashish Gosain | 92448 |  | 12 | 0 |  | 0 |  | 0 |  | 0
Specification Specialist (Desal) | Shanmuga Nathan J. | 29056 |  | 4 | 0 |  | 0 |  | 0 |  | 0
Financial expert | Hemanth Chadda | 36318 |  | 3 | 0 |  | 0 |  | 0 |  | 0
Commissioning Engineer | Santhosh Kumar | 100150 |  | 10 | 0 |  | 0 |  | 0 |  | 0
Social Communication Specialist | Rajesh Mishra | 154080 |  | 16 | 0 |  | 0 |  | 3 |  | 28890
Civil Engineer | Ramesh Senthil |  | 31374000 | 72 | 0 |  |  | 0 | 45 |  |  | 19608750
Construction Planner Cost Estimator | Naisa Sreenivasulu Reddy |  | 1200000 | 4 | 0 |  |  | 0 | 0 |  |  | 0
Quantity Surveyor - 1 | Vinod Chandra K C |  | 15000000 | 50 | 0 |  |  | 0 | 0 |  |  | 0
Secretary | TBN |  | 3660300 | 70 | 5 |  |  | 261450 | 12 |  |  | 627480
Contract management Specialist | TBN |  | 2614500 | 6 | 0 |  |  | 0 | 1.5 |  |  | 653625
Geo Technical Engineer | TBN |  | 2614500 | 6 | 1 |  |  | 435750 | 0 |  |  | 0
Office boy-1 | TBN |  | 1830150 | 70 | 5 |  |  | 130725 | 12 |  |  | 313740
Office boy-2 | TBN |  | 1830150 | 70 | 5 |  |  | 130725 | 12 |  |  | 313740
Office Manager & Travel & Visa processing officer | TBN |  | 7320600 | 70 | 5 |  |  | 522900 | 12 |  |  | 1254960
Accountant | TBN |  | 4880400 | 70 | 5 |  |  | 348600 | 12 |  |  | 836640
|  | 7259955 | 72324600 |  |  | 0 | 0 | 1830150 |  | 1602714 | 28890 | 23608935

## CP 4
CP1 Desalination Plant and CP2 Pumping Stations and Reservoirs
[5 empty] | Design + Tendering |  |  |  | Construction Supervision +DLP
Role | Name | Cost (US$) | Cost (INR) | Total Months | Input in CP4 | SMEC Intl (US$) | SMEC India (US$) | SMEC India (INR) | Input in CP4 | SMEC Intl (US$) | SMEC India (US$) | SMEC India (INR)
Project Manager | Dr Pararajasegram Dharmabalan | 2625070 |  | 70 | 6 | 225006 |  |  | 18 | 675018
Water Supply Engineer | Shane Farquharson | 583280 |  | 23 | 6 | 152160 |  |  | 12 | 304320
Mechanical Engineer (Desal) | Michael Morillon | 660000 |  | 15 | 0 | 0 |  |  | 0 | 0
Electrical Engineer (Desal) | Sergio de Bastos Vilar Magalhaes Paulo | 328300 |  | 25 | 0 | 0 |  |  | 0 | 0
Pipeline Engineer | John Goullee | 1582140 |  | 70 | 3 | 67806 |  |  | 12 | 271224
Contract Specialist (Desal) | Roderick Mackenzie | 399663 |  | 9 | 0 | 0 |  |  | 0 | 0
Monitoring and Control Expert (Desal) | Manikandan Ganesh Shoranur | 211860 |  | 11 | 0 | 0 |  |  | 0 | 0
Civil and Structure Engineer (Desal) | Dr. D. Elancherian | 457590 |  | 42 | 0 |  | 0 |  | 0 |  | 0
Monitoring and Control Expert (Distribution) | Ashish Gosain | 92448 |  | 12 | 3 |  | 23112 |  | 4 |  | 30816
Specification Specialist (Desal) | Shanmuga Nathan J. | 29056 |  | 4 | 0 |  | 0 |  | 0 |  | 0
Financial expert | Hemanth Chadda | 36318 |  | 3 | 0 |  | 0 |  | 0 |  | 0
Commissioning Engineer | Santhosh Kumar | 100150 |  | 10 | 0 |  | 0 |  | 0 |  | 0
Social Communication Specialist | Rajesh Mishra | 154080 |  | 16 | 1 |  | 9630 |  | 5 |  | 48150
Civil Engineer | Ramesh Senthil |  | 31374000 | 72 | 3 |  |  | 1307250 | 12 |  |  | 5229000
Construction Planner Cost Estimator | Naisa Sreenivasulu Reddy |  | 1200000 | 4 | 0 |  |  | 0 | 0 |  |  | 0
Quantity Surveyor - 1 | Vinod Chandra K C |  | 15000000 | 50 | 0 |  |  | 0 | 0 |  |  | 0
Secretary | TBN |  | 3660300 | 70 | 6 |  |  | 313740 | 12 |  |  | 627480
Contract management Specialist | TBN |  | 2614500 | 6 | 0 |  |  | 0 | 2 |  |  | 871500
Geo Technical Engineer | TBN |  | 2614500 | 6 | 2 |  |  | 871500 | 0 |  |  | 0
Office boy-1 | TBN |  | 1830150 | 70 | 6 |  |  | 156870 | 12 |  |  | 313740
Office boy-2 | TBN |  | 1830150 | 70 | 6 |  |  | 156870 | 12 |  |  | 313740
Office Manager & Travel & Visa processing officer | TBN |  | 7320600 | 70 | 6 |  |  | 627480 | 12 |  |  | 1254960
Accountant | TBN |  | 4880400 | 70 | 6 |  |  | 418320 | 12 |  |  | 836640
|  | 7259955 | 72324600 |  |  | 444972 | 32742 | 3852030 |  | 1250562 | 78966 | 9447060

## CP 5
CP1 Desalination Plant and CP2 Pumping Stations and Reservoirs
[5 empty] | Design + Tendering |  |  |  | Construction Supervision +DLP
Role | Name | Cost (US$) | Cost (INR) | Total Months | Input in CP5 | SMEC Intl (US$) | SMEC India (US$) | SMEC India (INR) | Input in CP5 | SMEC Intl (US$) | SMEC India (US$) | SMEC India (INR)
Project Manager | Dr Pararajasegram Dharmabalan | 2625070 |  | 70 | 0 | 0 |  |  | 6 | 225006
Water Supply Engineer | Shane Farquharson | 583280 |  | 23 | 0 | 0 |  |  | 0 | 0
Mechanical Engineer (Desal) | Michael Morillon | 660000 |  | 15 | 0 | 0 |  |  | 0 | 0
Electrical Engineer (Desal) | Sergio de Bastos Vilar Magalhaes Paulo | 328300 |  | 25 | 0 | 0 |  |  | 3 | 39396
Pipeline Engineer | John Goullee | 1582140 |  | 70 | 0 | 0 |  |  | 0 | 0
Contract Specialist (Desal) | Roderick Mackenzie | 399663 |  | 9 | 0 | 0 |  |  | 0 | 0
Monitoring and Control Expert (Desal) | Manikandan Ganesh Shoranur | 211860 |  | 11 | 0 | 0 |  |  | 0 | 0
Civil and Structure Engineer (Desal) | Dr. D. Elancherian | 457590 |  | 42 | 0 |  | 0 |  | 0 |  | 0
Monitoring and Control Expert (Distribution) | Ashish Gosain | 92448 |  | 12 | 0 |  | 0 |  | 0 |  | 0
Specification Specialist (Desal) | Shanmuga Nathan J. | 29056 |  | 4 | 0 |  | 0 |  | 0 |  | 0
Financial expert | Hemanth Chadda | 36318 |  | 3 | 0 |  | 0 |  | 0 |  | 0
Commissioning Engineer | Santhosh Kumar | 100150 |  | 10 | 0 |  | 0 |  | 0 |  | 0
Social Communication Specialist | Rajesh Mishra | 154080 |  | 16 | 0.5 |  | 4815 |  | 2.5 |  | 24075
Civil Engineer | Ramesh Senthil |  | 31374000 | 72 | 0 |  |  | 0 | 0 |  |  | 0
Construction Planner Cost Estimator | Naisa Sreenivasulu Reddy |  | 1200000 | 4 | 0 |  |  | 0 | 0 |  |  | 0
Quantity Surveyor - 1 | Vinod Chandra K C |  | 15000000 | 50 | 3 |  |  | 900000 | 0 |  |  | 0
Secretary | TBN |  | 3660300 | 70 | 5 |  |  | 261450 | 12 |  |  | 627480
Contract management Specialist | TBN |  | 2614500 | 6 | 0 |  |  | 0 | 0.5 |  |  | 217875
Geo Technical Engineer | TBN |  | 2614500 | 6 | 1 |  |  | 435750 | 0 |  |  | 0
Office boy-1 | TBN |  | 1830150 | 70 | 5 |  |  | 130725 | 12 |  |  | 313740
Office boy-2 | TBN |  | 1830150 | 70 | 5 |  |  | 130725 | 12 |  |  | 313740
Office Manager & Travel & Visa processing officer | TBN |  | 7320600 | 70 | 5 |  |  | 522900 | 12 |  |  | 1254960
Accountant | TBN |  | 4880400 | 70 | 5 |  |  | 348600 | 12 |  |  | 836640
|  | 7259955 | 72324600 |  |  | 0 | 4815 | 2730150 |  | 264402 | 24075 | 3564435

## Lists (hidden)
Project Planner |  | Rules | AC1 | ACT
Class |  | Client Sector Grooup | NC1 | NSW
EOI |  | Defence | PA1 | NSW
Estimate |  | Industrial-Manufac-Chemical | NS1 | NSW
Marketing |  | IT and Communications | GR1 | NSW
Overhead |  | Mining, Oil and Gas | WS1 | NSW
Project |  | Primary Industries | NT1 | NTE
Proposal |  | Public Sector Advisory | CN1 | QLD
|  | Social Infrastructure | GC1 | QLD
Location |  | Transport Infrastructure | QL1 | QLD
001 New South Wales |  | Urban Infrastructure Dev-Mgt | SC1 | QLD
002 Australian Cap. Territory |  | Utilities Infrastructure | TV1 | QLD
003 Queensland |  |  | SA1 | SAO
004 Victoria |  | Services | GL1 | VIC
005 South Australia |  | Conceptualisation | TR1 | VIC
006 Western Australia |  | Construction | VI1 | VIC
007 Tasmania |  | Design | WA1 | WAU
008 Northern Territory |  | Feasibility | NZ1 | NZL
009 New Zealand |  | Operations and Maintenance
Planning
project type |  | Social Services
Alliance |  | Internal
Inputs based
Fixed Price (lump sum) |  | Customer Type
Time and Material |  | Chinese Contractor
N/A Internal Projects |  | Concessionaries
Developers (urban and others)
Industry Type |  | Equipment Supplier
Agriculture, Forestry and Fishing |  | Financiers (Non IFI)
Defence |  | IFIs Direct
Industrial, Manufacturing and Chemical |  | Other Contractors
IT and Communications |  | Private Enterprises & Individuals
Mining |  | Professional Services
Oil and Gas |  | Public Sector (Government departments, national, regional & local agencies)
Private Sector Construction
Public Sector - Construction
Public Sector - Non Construction
Utilities
N/A (Internal Projects)
Funding Source
Foreign Aid or Development Agencies
Public Sector
Intercompany
Private Sector
Work Type
Asset Mgmt
Commissioning
Construction Supervision
Contract Admin/Mgmt
Cost Estimates
Design
Institutional Strengthening
Investigation/Studies
Other
Planning
Procurement
Project Mgmt
Survey
Technical Review/Audit
Tender Document/Analysis
Training/HRD
Office
Canberra | ACTAC1
Cairns | QLDCN1
Gold Cost | QLDGC1
Geelong | VICGL1
Grafton | NSWGR1
Newcastle | NSWNC1
North Sydney | NSWNS1
Northern Territory (Darwin) | NTENT1
Parramatta | NSWPA1
Brisbane | QLDQL1
Adelaide | SAOSA1
Sunshine Coast | QLDSC1
Traralgon | VICTR1
Townsville | QLDTV1
Melbourne | VICVI1
Perth | WAUWA1
Western Sydney ( Campbelltown) | NSWWS1
Wollongong | NSWWO1
SMEC Testing Subsidiary | NSWSTS1
International- Main country office
Other- Not listed
Function
AP - Airports
AM - Asset Management
EN - Environment
GT - Geotechnics and Tunnels
HD- Hydropower and Dams (International only)
LG - Advisory Services
MN - Resources and Mining
PE - Power and Energy
PH - Ports and Marine
RH - Roads and Highways
RL - Rail
UD - Urban Development
WT - Water
Subfunction
GT GEOTECHNICS | GTGEOGEO
GT TUNNELS | GTTUNTUN
AM Asset Management | AMAMMAMM
PE ASSET MGT INSTIT. | PEAMIAMI
PE CAD | PECADCAD
PE DISTRIBUTION | PEDISDIS
PE THERMAL GENERATION | PETMGTMG
PE RENEWABLE ENERGY | PEREEREE
PE POWER SYSTEM STUDIES | PESYSSYS
PE TRANSMISSION | PETRNTRN
RH ASSET MAINT MGT | RHAMMAMM
RH BRIDGES | RHBRDBRD
RH CONSTRUCTION MGT | RHCMMCMM
RH ROAD HWAY DESIGN | RHRHDRHD
RH ROAD HWAY DESIGN CAD | RHRHDCAD
RH PROJ DEVELOP + TRANS PLAN | RHDPLDPL
RH TRAFF AND TPORT STU | RHTTSTTS
RL STRUCTURES | RLSTRSTR
RL RAILWAYS | RLRWYRWY
PH PORTS + HARBOURS | PHPHAPHA
AP AIRPORTS | APAPTAPT
WT CAD | WTCADCAD
WT DAM | WTDAMDAM
WT IRRIGATION | WTIRRIRR
WT WATER INFRASTR. | WTURIURI
WT WATER RESOURCES | WTWARWAR
EN ENVIR. STUD | ENENSENS
EN PLAN STUDIES | ENPLSPLS
EN SITE CONTAMIN | ENSCOSCO
EN SUSTAINABLE DEV | ENSUDSUD
UD ENGINEERING | UDENGENG
UD INFRASTRUCTURE | UDINFINF
UD LANDSCAPE ARCHITECT | UDLARLAR
UD PROJECT DEVELOPMENT | UDPDVPDV
UD PROJECT MANAGEM | UDPJMPJM
UD PLANNING + URBAN DE | UDPUDPUD
UD SURVEY | UDSURSUR
MN MINING AND RESOURCES | MNMNRMNR

## Org Data (hidden)
Functional Group Code | Functional Group Name | Function | Stream | Org Unit | discipline
AD | ADVISORY | AD - ADVISORY | AD AMM ASSET MNGT SERVICES | ADAMMAMS | AD
AM | ASSET MANAGEMENT | AM - ASSET MANAGEMENT | AD ENV ENVIRONMENT | ADENVENV | AD
AP | AIRPORTS | AP - AIRPORTS | AD GOV CAPACITY BUILDING | ADGOVCAP | AD
AS | ACQUISITION & SUSTAINMENT | AS - ACQUISITION & SUSTAINMENT | AD GOV GOVERNANCE | ADGOVGOV | AD
BI | BUILDINGS AND INDUSTRIAL | BI - BUILDINGS AND INDUSTRIAL | AD GOV ORGAN REFORM | ADGOVORG | AD
CM | CONSTRUCTION MANAGEMENT | CM - CONSTRUCTION MANAGEMENT | AD GOV SERVICE DELIVERY | ADGOVSER | AD
CP | CORPORATE | CP - CORPORATE | AD TSP TRANSPORT | ADTSPTSP | AD
DI | DEFENCE INFRASTRUCTURE | DI - DEFENCE INFRASTRUCTURE | AD WSM WASTE MANAGEMENT | ADWSMWSM | AD
ED | EDUCATION | ED - EDUCATION | AD WWW ADVISORY SERVICES | ADWWWADV | AD
EN | ENVIRONMENT | EN - ENVIRONMENT | AD WWW OPS AND MAINTENANCE | ADWWWOPM | AD
FM | FACILITIES MANAGEMENT | FM - FACILITIES MANAGEMENT | AD WWW WATER AND WASTE WATER | ADWWWWWW | AD
GE | GEOTECHNICS | GE - GEOTECHNICS | AM AMM ASSET MANAGEMENT | AMAMMAMM | AM
GF | GREENFIELDS | GF - GREENFIELDS | AP APT AIRPORTS | APAPTAPT | AP
GI | GEOTECHNICALINVESTIGATION & TESTING | GI - GEOTECHNICALINVESTIGATION & TESTING | AS ACQ ACQUISITION & SUSTAINMENT | ASACQACQ | AS
GV | GOVERNMENT | GV - GOVERNMENT | BI BLD BUILDINGS | BIBLDBLD | BI
HD | DAMS & HYDRO | HD - DAMS & HYDRO | BI NST INDUSTRIAL | BINSTNST | BI
HR | HEALTH & RETIREMENT | HR - HEALTH & RETIREMENT | CM CMM CONSTRUCTION MGT | CMCMMCMM | CM
OP | OPERATIONS | OP - OPERATIONS | CP ADM OVERHEAD | CPADMOVE | CP
PE | POWER & ENERGY | PE - POWER & ENERGY | CP BSD OVERHEAD | CPBSDOVE | CP
PH | PORTS AND MARINE | PH - PORTS AND MARINE | CP CAF OVERHEAD | CPCAFOVE | CP
RE | RESOURCES | RE - RESOURCES | CP HRM OVERHEAD | CPHRMOVE | CP
RH | ROADS&HIGHWAYS | RH - ROADS & HIGHWAYS | CP ITC OVERHEAD | CPITCOVE | CP
RL | RAIL AND METRO | RL - RAIL AND METRO | CP LEG OVERHEAD | CPLEGOVE | CP
SC | SMARTCITIES | SC - SMARTCITIES | CP QAL OVERHEAD | CPQALOVE | CP
SD | SOCIAL DEVELOPMENT | SD - SOCIAL DEVELOPMENT | DI DIN INFRASTRUCTURE | DIDINDIN | DI
TN | TUNNELING | TN - TUNNELING | ED ENG COMP AID DESIGN | EDENGCAD | ED
TP | TRANSPORT PLANNING, LOGISTICS & Analysis | TP - TRANSPORT PLANNING, LOGISTICS & Analysis | ED ENG ENGINEERING | EDENGENG | ED
UA | UNALLOCATED | UA - UNALLOCATED | ED INF INFRASTRUCTURE | EDINFINF | ED
UR | URBAN RENEWAL | UR - URBAN RENEWAL | ED LAR COMP AID DESIGN | EDLARCAD | ED
WI | WATER INFRASTRUCTURE | WI - WATER INFRASTRUCTURE | ED LAR LANDSCAPE ARCHITECT | EDLARLAR | ED
WR | WATER RESOURCES | WR - WATER RESOURCES | ED PDV PROJECT DEVELOPMENT | EDPDVPDV | ED
WS | WASTE | WS - WASTE | ED PJM PROJECT MANAGEMENT | EDPJMPJM | ED
|  |  | ED PRO PAID FEASABILITIES | EDPROPRO | ED
|  |  | ED PRO UNPAID FEASABILITIES | EDPROUND | ED
|  |  | ED PUD PLANNING + URBAN DE | EDPUDPUD | ED
|  |  | ED SUR COMP AID DESIGN | EDSURCAD | ED
|  |  | ED SUR SURVEY | EDSURSUR | ED
|  |  | EN ENS ENVIR. STUD | ENENSENS | EN
|  |  | EN PLS PLAN STUDIES | ENPLSPLS | EN
|  |  | EN SCO SITE CONTAMIN | ENSCOSCO | EN
|  |  | EN SUD SUSTAINABLE DEV | ENSUDSUD | EN
|  |  | FM FCM FACILITIES MANAGEMENT | FMFCMFCM | FM
|  |  | GE GEO GEOTECHNICS | GEGEOGEO | GE
|  |  | GF DESIGN | GFDESDES | GF
|  |  | GF ENG COMP AID DESIGN | GFENGCAD | GF
|  |  | GF ENG ENGINEERING | GFENGENG | GF
|  |  | GF INF INFRASTRUCTURE | GFINFINF | GF
|  |  | GF LAR COMP AID DESIGN | GFLARCAD | GF
|  |  | GF LAR LANDSCAPE ARCHITECT | GFLARLAR | GF
|  |  | GF PDV PROJECT DEVELOPMENT | GFPDVPDV | GF
|  |  | GF PJM PROJECT MANAGEMENT | GFPJMPJM | GF
|  |  | GF PRO PAID FEASABILITIES | GFPROPRO | GF
|  |  | GF PRO UNPAID FEASABILITIES | GFPROUND | GF
|  |  | GF PUD COMP AID DESIGN | GFPUDCAD | GF
|  |  | GF PUD PLANNING + URBAN DE | GFPUDPUD | GF
|  |  | GF SUR COMP AID DESIGN | GFSURCAD | GF
|  |  | GF SUR SURVEY | GFSURSUR | GF
|  |  | GI INV INVESTIGATION & TESTING | GIINVINV | GI
|  |  | GV ENG COMP AID DESIGN | GVENGCAD | GV
|  |  | GV ENG ENGINEERING | GVENGENG | GV
|  |  | GV INF INFRASTRUCTURE | GVINFINF | GV
|  |  | GV LAR COMP AID DESIGN | GVLARCAD | GV
|  |  | GV LAR LANDSCAPE ARCHITECT | GVLARLAR | GV
|  |  | GV PDV PROJECT DEVELOPMENT | GVPDVPDV | GV
|  |  | GV PJM PROJECT MANAGEMENT | GVPJMPJM | GV
|  |  | GV PRO PAID FEASABILITIES | GVPROPRO | GV
|  |  | GV PRO UNPAID FEASABILITIES | GVPROUND | GV
|  |  | GV PUD PLANNING + URBAN DE | GVPUDPUD | GV
|  |  | GV SUR COMP AID DESIGN | GVSURCAD | GV
|  |  | GV SUR SURVEY | GVSURSUR | GV
|  |  | HD CAD COMP AID DESIGN | HDCADCAD | HD
|  |  | HD CMT CONSTRUCTION MGMT. | HDCMTCMT | HD
|  |  | HD DAM DAMS | HDDAMDAM | HD
|  |  | HD GLY GEOLOGY | HDGLYGLY | HD
|  |  | HD HYD HYDROPOWER | HDHYDHYD | HD
|  |  | HD STR STRUCTURES | HDSTRSTR | HD
|  |  | HD UGW UNDERGRND WORKS | HDUGWUGW | HD
|  |  | HR ENG COMP AID DESIGN | HRENGCAD | HR
|  |  | HR ENG ENGINEERING | HRENGENG | HR
|  |  | HR INF INFRASTRUCTURE | HRINFINF | HR
|  |  | HR LAR COMP AID DESIGN | HRLARCAD | HR
|  |  | HR LAR LANDSCAPE ARCHITECT | HRLARLAR | HR
|  |  | HR PDV PROJECT DEVELOPMENT | HRPDVPDV | HR
|  |  | HR PJM PROJECT MANAGEMENT | HRPJMPJM | HR
|  |  | HR PRO PAID FEASABILITIES | HRPROPRO | HR
|  |  | HR PRO UNPAID FEASABILITIES | HRPROUND | HR
|  |  | HR PUD PLANNING + URBAN DE | HRPUDPUD | HR
|  |  | HR SUR COMP AID DESIGN | HRSURCAD | HR
|  |  | HR SUR SURVEY | HRSURSUR | HR
|  |  | OP OPE OPERATIONS | OPOPEOPE | OP
|  |  | PE AMI INDUSTRIAL + GAS | PEAMIAMI | PE
|  |  | PE CAD CAD | PECADCAD | PE
|  |  | PE DIS T + D + SUBS | PEDISDIS | PE
|  |  | PE REE RENEWABLE ENERGY | PEREEREE | PE
|  |  | PE SYS SYSTEM STUDIES | PESYSSYS | PE
|  |  | PE TMG THERMAL GENERATION | PETMGTMG | PE
|  |  | PE TRN T + D + SUBS | PETRNTRN | PE
|  |  | PH PHA PORTS + MARINE | PHPHAPHA | PH
|  |  | RE MNR MINING SERVICES | REMNRMNR | RE
|  |  | RE OGS OIL AND GAS SERVICES | REOGSOGS | RE
|  |  | RH BRD BRIDGES | RHBRDBRD | RH
|  |  | RH AMM ASSET MAINT MGT | RHAMMAMM | RH
|  |  | RH BRD COMP AID DESIGN | RHBRDCAD | RH
|  |  | RH RHD BRIDGES | RHRHDBRD | RH
|  |  | RH RHD COMP AID DESIGN | RHRHDCAD | RH
|  |  | RH RHD ROAD HWAY DESIGN | RHRHDRHD | RH
|  |  | RL RWY COMP AID DESIGN | RLRWYCAD | RL
|  |  | RL RWY RAILWAYS | RLRWYRWY | RL
|  |  | RL STR STRUCTURES | RLSTRSTR | RL
|  |  | SC SCM SMART CITIES | SCSCMSCM | SC
|  |  | SD CBI CAP BLD + INST STRG | SDCBICBI | SD
|  |  | SD EDU EDUCATION | SDEDUEDU | SD
|  |  | SD GPS GOV. + PUB SEC REF | SDGPSGPS | SD
|  |  | SD HEA HEALTH | SDHEAHEA | SD
|  |  | SD HRM HRM + TRAINING | SDHRMHRM | SD
|  |  | TN TUN TUNNELING | TNTUNTUN | TN
|  |  | TP DPL PROJ DEVELOP + TRANS PLAN | TPDPLDPL | TP
|  |  | TP TTS TRAFF AND TPORT STU | TPTTSTTS | TP
|  |  | UR DESIGN | URDESDES | UR
|  |  | UR ENG COMP AID DESIGN | URENGCAD | UR
|  |  | UR ENG ENGINEERING | URENGENG | UR
|  |  | UR INF INFRASTRUCTURE | URINFINF | UR
|  |  | UR LAR COMP AID DESIGN | URLARCAD | UR
|  |  | UR LAR LANDSCAPE ARCHITECT | URLARLAR | UR
|  |  | UR PDV PROJECT DEVELOPMENT | URPDVPDV | UR
|  |  | UR PJM PROJECT MANAGEMENT | URPJMPJM | UR
|  |  | UR PRO PAID FEASABILITIES | URPROPRO | UR
|  |  | UR PRO UNPAID FEASABILITIES | URPROUND | UR
|  |  | UR PUD PLANNING + URBAN DE | URPUDPUD | UR
|  |  | UR SUR COMP AID DESIGN | URSURCAD | UR
|  |  | UR SUR SURVEY | URSURSUR | UR
|  |  | WI CAD COMP AID DESIGN | WICADCAD | WI
|  |  | WI URI COMP AID DESIGN | WIURICAD | WI
|  |  | WI URI WATER INFRASTR. | WIURIURI | WI
|  |  | WR IRR IRRIGATION | WRIRRIRR | WR
|  |  | WR WAR COMP AID DESIGN | WRWARCAD | WR
|  |  | WR WAR WATER RESOURCES | WRWARWAR | WR
|  |  | WS WAS WASTE | WSWASWAS | WS

## Sheet1 (hidden)
Functional Group Code | Functional Group Name | combined | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
AD | ADVISORY | AD - ADVISORY | AD AMM ASSET MNGT SERVICES | AD ENV ENVIRONMENT | AD GOV CAPACITY BUILDING | AD GOV GOVERNANCE | AD GOV ORGAN REFORM | AD GOV SERVICE DELIVERY | AD TSP TRANSPORT | AD WSM WASTE MANAGEMENT | AD WWW ADVISORY SERVICES | AD WWW OPS AND MAINTENANCE | AD WWW WATER AND WASTE WATER
AM | ASSET MANAGEMENT | AM - ASSET MANAGEMENT | AM AMM ASSET MANAGEMENT
AP | AIRPORTS | AP - AIRPORTS | AP APT AIRPORTS
AS | ACQUISITION & SUSTAINMENT | AS - ACQUISITION & SUSTAINMENT | AS ACQ ACQUISITION & SUSTAINMENT
BI | BUILDINGS AND INDUSTRIAL | BI - BUILDINGS AND INDUSTRIAL | BI BLD BUILDINGS | BI NST INDUSTRIAL
CM | CONSTRUCTION MANAGEMENT | CM - CONSTRUCTION MANAGEMENT | CM CMM CONSTRUCTION MGT
CP | CORPORATE | CP - CORPORATE | CP ADM OVERHEAD | CP BSD OVERHEAD | CP CAF OVERHEAD | CP HRM OVERHEAD | CP ITC OVERHEAD | CP LEG OVERHEAD | CP QAL OVERHEAD
DI | DEFENCE INFRASTRUCTURE | DI - DEFENCE INFRASTRUCTURE | DI DIN INFRASTRUCTURE
ED | EDUCATION | ED - EDUCATION | ED ENG COMP AID DESIGN | ED ENG ENGINEERING | ED INF INFRASTRUCTURE | ED LAR COMP AID DESIGN | ED LAR LANDSCAPE ARCHITECT | ED PDV PROJECT DEVELOPMENT | ED PJM PROJECT MANAGEMENT | ED PRO PAID FEASABILITIES | ED PRO UNPAID FEASABILITIES | ED PUD PLANNING + URBAN DE | ED SUR COMP AID DESIGN | ED SUR SURVEY
EN | ENVIRONMENT | EN - ENVIRONMENT | EN ENS ENVIR. STUD | EN PLS PLAN STUDIES | EN SCO SITE CONTAMIN | EN SUD SUSTAINABLE DEV
FM | FACILITIES MANAGEMENT | FM - FACILITIES MANAGEMENT | FM FCM FACILITIES MANAGEMENT
GE | GEOTECHNICS | GE - GEOTECHNICS | GE GEO GEOTECHNICS
GF | GREENFIELDS | GF - GREENFIELDS | GF DESIGN | GF ENG COMP AID DESIGN | GF ENG ENGINEERING | GF INF INFRASTRUCTURE | GF LAR COMP AID DESIGN | GF LAR LANDSCAPE ARCHITECT | GF PDV PROJECT DEVELOPMENT | GF PJM PROJECT MANAGEMENT | GF PRO PAID FEASABILITIES | GF PRO UNPAID FEASABILITIES | GF PUD COMP AID DESIGN | GF PUD PLANNING + URBAN DE | GF SUR COMP AID DESIGN | GF SUR SURVEY
GI | GEOTECHNICALINVESTIGATION & TESTING | GI - GEOTECHNICALINVESTIGATION & TESTING | GI INV INVESTIGATION & TESTING
GV | GOVERNMENT | GV - GOVERNMENT | GV ENG COMP AID DESIGN | GV ENG ENGINEERING | GV INF INFRASTRUCTURE | GV LAR COMP AID DESIGN | GV LAR LANDSCAPE ARCHITECT | GV PDV PROJECT DEVELOPMENT | GV PJM PROJECT MANAGEMENT | GV PRO PAID FEASABILITIES | GV PRO UNPAID FEASABILITIES | GV PUD PLANNING + URBAN DE | GV SUR COMP AID DESIGN | GV SUR SURVEY
HD | DAMS & HYDRO | HD - DAMS & HYDRO | HD CAD COMP AID DESIGN | HD CMT CONSTRUCTION MGMT. | HD DAM DAMS | HD GLY GEOLOGY | HD HYD HYDROPOWER | HD STR STRUCTURES | HD UGW UNDERGRND WORKS
HR | HEALTH & RETIREMENT | HR - HEALTH & RETIREMENT | HR ENG COMP AID DESIGN | HR ENG ENGINEERING | HR INF INFRASTRUCTURE | HR LAR COMP AID DESIGN | HR LAR LANDSCAPE ARCHITECT | HR PDV PROJECT DEVELOPMENT | HR PJM PROJECT MANAGEMENT | HR PRO PAID FEASABILITIES | HR PRO UNPAID FEASABILITIES | HR PUD PLANNING + URBAN DE | HR SUR COMP AID DESIGN | HR SUR SURVEY
OP | OPERATIONS | OP - OPERATIONS | OP OPE OPERATIONS
PE | POWER & ENERGY | PE - POWER & ENERGY | PE AMI INDUSTRIAL + GAS | PE CAD CAD | PE DIS T + D + SUBS | PE REE RENEWABLE ENERGY | PE SYS SYSTEM STUDIES | PE TMG THERMAL GENERATION | PE TRN T + D + SUBS
PH | PORTS AND MARINE | PH - PORTS AND MARINE | PH PHA PORTS + MARINE
RE | RESOURCES | RE - RESOURCES | RE MNR MINING SERVICES | RE OGS OIL AND GAS SERVICES
RH | ROADS&HIGHWAYS | RH - ROADS & HIGHWAYS | RH BRD BRIDGES | RH AMM ASSET MAINT MGT | RH BRD COMP AID DESIGN | RH RHD BRIDGES | RH RHD COMP AID DESIGN | RH RHD ROAD HWAY DESIGN
RL | RAIL AND METRO | RL - RAIL AND METRO | RL RWY COMP AID DESIGN | RL RWY RAILWAYS | RL STR STRUCTURES
SC | SMARTCITIES | SC - SMARTCITIES | SC SCM SMART CITIES
SD | SOCIAL DEVELOPMENT | SD - SOCIAL DEVELOPMENT | SD CBI CAP BLD + INST STRG | SD EDU EDUCATION | SD GPS GOV. + PUB SEC REF | SD HEA HEALTH | SD HRM HRM + TRAINING
TN | TUNNELING | TN - TUNNELING | TN TUN TUNNELING
TP | TRANSPORT PLANNING, LOGISTICS & Analysis | TP - TRANSPORT PLANNING, LOGISTICS & Analysis | TP DPL PROJ DEVELOP + TRANS PLAN | TP TTS TRAFF AND TPORT STU
UR | URBAN RENEWAL | UR - URBAN RENEWAL | UR DESIGN | UR ENG COMP AID DESIGN | UR ENG ENGINEERING | UR INF INFRASTRUCTURE | UR LAR COMP AID DESIGN | UR LAR LANDSCAPE ARCHITECT | UR PDV PROJECT DEVELOPMENT | UR PJM PROJECT MANAGEMENT | UR PRO PAID FEASABILITIES | UR PRO UNPAID FEASABILITIES | UR PUD PLANNING + URBAN DE | UR SUR COMP AID DESIGN | UR SUR SURVEY
WI | WATER INFRASTRUCTURE | WI - WATER INFRASTRUCTURE | WI CAD COMP AID DESIGN | WI URI COMP AID DESIGN | WI URI WATER INFRASTR.
WR | WATER RESOURCES | WR - WATER RESOURCES | WR IRR IRRIGATION | WR WAR COMP AID DESIGN | WR WAR WATER RESOURCES
WS | WASTE | WS - WASTE | WS WAS WASTE