## SMEC India
| Total Billing | Biiling Rate |  | DESIGN including Tendering (Input months) |  |  |  | Cost (US$) | Construction Supervision including DLP |  |  |  | Cost | Input Months
Role | Cost (US$) | USD |  | CP1& CP2 | CP3 | CP4 | CP5 |  | CP1&CP2 | CP3 | CP4 | CP5
Project Manager | 2625070 | 37500 |  | 8 | 0 | 6 | 0 | 37188637.5 | 20 | 12 | 18 | 6 | 148754550 | 70
Water Supply Engineer | 583280 | 25360 |  | 5 | 0 | 6 | 0 | 19760271.08 | 0 | 0 | 12 |  | 21556659.36 | 23
Mechanical Engineer (Desal) | 660000 | 44000 |  | 5 | 0 | 0 | 0 | 15583810 | 10 |  |  |  | 31167620 | 15
Electrical Engineer (Desal) | 328300 | 13132 |  | 7 |  |  |  | 6511482.502 | 15 |  |  | 3 | 16743812.148 | 25
Pipeline Engineer | 1582140 | 22602 |  | 1 | 0 | 3 |  | 6404095.884 | 3 | 51 | 12 |  | 105667582.086 | 70
Contract Specialist (Desal) | 399663 | 44407 |  | 8 |  |  |  | 25164736.388 | 1 |  |  |  | 3145592.0485 | 9
Monitoring and Control Expert (Desal) | 211860 | 19260 |  | 3 |  |  |  | 4092875.19 | 8 |  |  |  | 10914333.84 | 11
| 6390313 | [6 empty] | 114705908.544 |  |  |  |  | 337950149.4825
|  |  | INR | 83186519.451 | 0 | 31519389.093 | 0 |  | 117110419.5915 | 113528197.521 | 88582909.512 | 18728622.858
|  |  | AUD | 1707440.8754 | 0 | 646949.694 | 0 |  | 2403744.2445 | 2330217.5189 | 1818204.2182 | 384413.4413
1815907.0299
452656058.0265
9290969.9923
|  |  |  | DESIGN including Tendering |  |  |  | Cost (US$) | Cost (INR) | Construction Supervision including DLP |  |  |  | Cost (US$) | Cost (INR) | Input Months
Role | Name | Rate (USD) | Rate (INR) | CP1& CP2 | CP3 | CP4 | CP5 |  |  | CP1&CP2 | CP3 | CP4 | CP5
Civil and Structure Engineer (Desal) | Dr. D. Elancherian | 10895 |  | 6 |  |  |  | 4630516.635 |  | 36 |  |  |  | 27783099.81 |  | 42
Monitoring and Control Expert (Distribution) | Ashish Gosain | 7704 |  | 2 |  | 3 |  | 2728583.46 |  | 3 |  | 4 |  | 3820016.844 |  | 12
Specification Specialist (Desal) | Sethuraman | 7264 |  | 3 |  |  |  | 1543647.216 |  | 1 |  |  |  | 514549.072 |  | 4
Financial expert | Hemanth Chadda | 12106 |  | 3 |  |  |  | 2572603.689 | [5 empty] | 0 |  | 3
Commissioning Engineer | Santhosh Kumar | 10015 |  | 0 |  |  |  | 0 |  | 10 |  |  |  | 7094175.325 |  | 10
Social Communication Specialist | Rajesh Mishra | 9630 |  | 1 | 0 | 1 | 0.5 | 1705364.6625 |  | 3 | 3 | 5 | 2.5 | 9208969.1775 |  | 16
Civil Engineer | Ramesh Senthil |  | 435750 | 6 | 0 | 3 |  |  | 3921750 | 6 | 45 | 12 |  |  | 27452250 | 72
Construction Planner Cost Estimator | Naisa Sreenivasulu Reddy |  | 300000 | 4 |  |  |  |  | 1200000 | [5 empty] | 0 | 4
Quantity Surveyor - 1 | Vinod Chandra K C |  | 300000 | 5 |  |  | 3 |  | 2400000 | 42 |  |  |  |  | 12600000 | 50
Secretary | TBN |  | 52290 | 6 | 5 | 6 | 5 |  | 1150380 | 12 | 12 | 12 | 12 |  | 2509920 | 70
Contract management Specialist | TBN |  | 435750 | [5 empty] | 0 | 2 | 1.5 | 2 | 0.5 |  | 2614500 | 6
Geo Technical Engineer | TBN |  | 435750 | 2 | 1 | 2 | 1 |  | 2614500 | [5 empty] | 0 | 6
Office boy-1 | TBN |  | 26145 | 6 | 5 | 6 | 5 |  | 575190 | 12 | 12 | 12 | 12 |  | 1254960 | 70
Office boy-2 | TBN |  | 26145 | 6 | 5 | 6 | 5 |  | 575190 | 12 | 12 | 12 | 12 |  | 1254960 | 70
Office Manager & Travel & Visa processing officer | TBN |  | 104580 | 6 | 5 | 6 | 5 |  | 2300760 | 12 | 12 | 12 | 12 |  | 5019840 | 70
Accountant | TBN |  | 69720 | 6 | 5 | 6 | 5 |  | 1533840 | 12 | 12 | 12 | 12 |  | 3346560 | 70
|  | 57614 | 2186130 |  |  |  |  | 13180715.6625 | 16271610 |  |  |  |  | 48420810.2285 | 56052990
|  |  | 148518 | 18379626.789 | 1830150 | 6171325.941 | 3071222.9325 |  |  | 58507971.878 | 25655372.595 | 15040656.093 | 5269799.6625
|  |  | 7859280 | 377250.1393 | 37564.6552 | 126669.2517 | 63038.2375 |  |  | 1200902.5427 | 526588.1075 | 308716.2581 | 108165.0177
133926125.891
2748894.2096